## Sheet_1
Updated 8/24/20
Project | Committee Leads | Project Description/Scope | Date Added to Project Plan | Estimated Completion Date | Status | Cost
Desert Road Bridge & Mallet Drive Bridge | Greg Michaud | Participate in MDOT and related project meetings, inform and advise CSC | 2019-10-01 |  | Awaiting design update from MDOT
Cousins River Bridge & Route 1 Multi-Purpose Path |  | Participate in MDOT and related project meetings, inform and advise CSC | 2019-10-01
Complete Streets Policy | Doug Leland | Develop Complete Street policy for Council review and approval | 2019-10-01 | 2020-10-01 | Approved by CSC & forwarded to Council
Bike Racks | Chief Nourse | Develop implementation plan for annual purchase and placement | 2019-10-01
Crosswalk Policy and Plan | Sally Walsh | Develop crosswalk protocols and specific plan for Main St. between West St. and Mallet Dr. | 2019-10-01
Education and Outreach Plan |  | Develop program for community education regarding Complete Streets and CS related topics | 2019-10-01
Multi-Modal Pathway Network Plan