## Active
As of April 6, 2021
Project | Committee Leads (Alternate in Parentheses) | Project Description/Scope | Date Added to Project Plan | Estimated Completion Date | Next Planned Steps (for next CSC mtg) | Milestones / Accomplishments | Key Contacts
Desert Road Bridge | Doug Leland (Adam Bliss) | Participate in MDOT and related project meetings, inform and advise CSC. | 2019-10-01 | 2022-2023 | Determine next steps with MDOT and communicate to CSC Committee | * Federal grant funding approved on September 4, 2019. * MDOT Design meeting held: CSC and ALC voted to locate multi-use path on north side and widended shoulder on south side of bridge at Maine DOT meeting. * MDOT cost-sharing meeting held October 6. * MDOT follow-up meeting scheduled for October 28. * Council approved 1/5/21 going to bond for $634k (Desert & Mallett) * FAQ distributed to Town Council 1/28 * FAQ version 2 distributed to Town Council 2/11 * Bond passed 3/9 * Advertising date 9/21 titled "Merrill Road Bridge" #5720 (MDOT) * $8,051,000 estimated cost
Mallett Drive Bridge | Doug Leland (Adam Bliss) | Participate in MDOT and related project meetings, inform and advise CSC. | 2019-10-01 | 2022-2023 | Determine next steps with MDOT and communicate to CSC Committee | * Federal grant funding approved on September 4, 2019. * Signal Warrant Analysis completed * MDOT Design meeting held: CSC and ALC voted to locate multi-use path on north side and widended shoulder on south side of bridge at Maine DOT meeting. * MDOT cost-sharing meeting held October 6. * MDOT follow-up meeting scheduled for October 28. * Meeting with VHB Engineeers to review Mallett Drive as part of PACTS as part of review to evaluate high crash locations (HCL) * Council approved 1/5/21 going to bond for $634k (Desert & Mallett) * FAQ distributed to Town Council 1/28 * FAQ version 2 distributed to Town Council 2/11 * Bond passed 3/9 * Advertising date 9/21 titled "Approach Road Interchange Bridge" #5721 (MDOT) * $7,218,000 estimated cost
Crosswalks | Sally Walsh | Develop crosswalk protocols and specific plan for Main St. between West St. and Mallett Dr. Build crosswalk competencies for committee to be leveraged in future projects. | 2019-10-01 | TBD | Update committee on contacts made and materials gathered. | * Create plan of existing crosswalks on Main Street from Mallett Drive to West Street. Include mapping, locations, visibility, functionality, use, pros, cons, MDOT compliance, tactile warning plates, signage, and accessibility * Greg, Doug L and Sally met to discuss establishing contacts for this effort. | Patrick Adams, Maine DOT BikePed Program Manager, (207) 624-3311 or at patrick.adams@maine.gov (reports to Steve Cole)
Bike Racks | Phil Wagner | Optimize bike rack usage and placement in the town | Oct 1, 2019 | TBD | Update committee on contact made with Andy Spaulding and any materials gathered. Seek further guidance from committee on the scope of the effort. | 1. Budget for bike racks for FY 2020. 2. Create existing inventory of bike racks (condition, type, locations, use frequency). 3. Existing Inventory completed. 2 existing locations; two U-racks at Town Hall and 1 rack at Train Station. | Andy Spaulding, Active Living Chair (207) 650-7889 andy.spaulding@wellvation.com
Public Peddlers and Food Trucks | Phil Wagner | Represents CSC in ongoing annual review and decision making regarding peddler carts and food trucks. Recommends and Manages changes/enhancements to Public Peddlers' Ordinances to ensure its ongoing currency | Jan 5, 2021 | TBD | Seek further guidance from committee on the scope of the effort. | CSC approved adding to workplan on 1/5/21.
Lower Main Street Beautification | Sally Walsh | Make recommendation to Town Council for welcoming and street calming road enhancements in the Lower Main Street area, in coordination with the LLBean reconstruction project | 2021-01-05 | 2021-06-30 | Update committee on progress to date | CSC approved adding to workplan on 1/5/21. Established connections to Freeport Visioning project Walkthrough (Sally, Greg, Doug) of LMS area to begin drafting questions and high levell recommendations | Tawni Whitney (twhitney@freeportmaine.com) Chip Gray (harraseeke@aol.com) / Mary Davis (maryhitt.davis@gmail.com)
Develop multi-use path solution for Yarmouth to Downtown | Liz McDonald | Through the Connect Freeport Committee, develop recommendations and submit proposed design for multi-use path | 2021-03-02 | TBD | Begin to make determinations on scope, timing and prioritizations of the four multi-use path proposals | CSC approved adding to workplan on 3/2/21
Develop multi-use path solution for Desert Road bridge to LLBean Distribution Center | Liz McDonald | Through the Connect Freeport Committee, develop recommendations and submit proposed design for multi-use path | 2021-03-02 | TBD | Begin to make determinations on scope, timing and prioritizations of the four multi-use path proposals | CSC approved adding to workplan on 3/2/21
Develop multi-use path solution for Mallett Drive bridge to US-1 | Liz McDonald | Through the Connect Freeport Committee, develop recommendations and submit proposed design for multi-use path | 2021-03-02 | TBD | Begin to make determinations on scope, timing and prioritizations of the four multi-use path proposals | CSC approved adding to workplan on 3/2/21
Develop multi-use path solution for Mallett Drive bridge to Pine Tree Academy | Liz McDonald | Through the Connect Freeport Committee, develop recommendations and submit proposed design for multi-use path | 2021-03-02 | TBD | Begin to make determinations on scope, timing and prioritizations of the four multi-use path proposals | CSC approved adding to workplan on 3/2/21
Investigate the need for and possible repurposing of the taxi stand on Main Street | Phil Wagner | Recommend alternative use for Main Street taxi stand parking space, obtain necessary approvals and ordinance changes as needed | 2021-03-02 | TBD | Establish target date and necessary steps to recommend and change use of the taxi stand area | CSC approved adding to workplan on 3/2/21
Cells highlighted in yellow reflect changes made from the previous month's submission

## Ongoing
As of April 6, 2021
Project | Committee Leads (Alternate in Parentheses) | Project Description/Scope | Date Added to Project Plan | Next Planned Steps (for next CSC mtg) | Milestones / Accomplishments
Active Living Committee Liaison | Doug Leland | Support the committee as CSC representative | 2020-12-01 | Define the scope and function of the role with respect to the two committees and prepare Active Living for sunset in 6/21 | Added to the workplan 1/5/21
Maintain Complete Streets Policy | Doug Leland | Ensure CS Policy is updated as needed, and re-approved by the Town Council annually | 2020-12-01 | Provide monthly updates to the Complete Streets committee as warranted | Added to the workplan 1/5/21
Quarterly Review of MDOT projects | Adam Bliss | Review changes to the MDOT project plan quarterly with the committee | April 6, 20201 | Review April, July, October in 2021

## Inactive or New
As of April 6, 2021
Project | Reason Inactive | Committee Leads (Alternate in Parentheses) | Project Description/Scope | Date Added to Project Plan | Estimated Completion Date | Milestones / Accomplishments
Cousins River Bridge & Route 1 Multi-Purpose Path | Project Not Started | TBD | Participate in MDOT and related project meetings, inform and advise CSC. | 2019-10-01 |  | Preliminary Design submitted to MDOT Project Manager.
Complete Streets Education and Communication | Greg Michaud |  | Develop program for community education regarding Complete Streets and CS related topics. | 2019-10-01 | 2021-07-01
Complete Streets Shared Documentation Repository | Greg Michaud |  | Develop comprehensive, shared documentation repository (Dropbox, GoogleDocs) for the Complete Streets Committee | 2021-04-06 | 2021-05-01
Coordination Map with Freeport Committees | Greg Michaud |  | Better understand, coordinate with and leverage other Freeport committees to complete mutual objectives | 2021-04-06 | 2021-08-01

## Complete
As of April 6, 2021
Project | Committee Leads (Alternate in Parentheses) | Project Description/Scope | Date Added to Project Plan | Completion Date | Final Disposition | Attachments
Write and Submit Complete Streets Policy | Doug Leland | Develop Complete Street policy for Council review and approval. | 2019-10-01 | 2020-12-05 | Town Council approved the policy on Dec 1, 2020
Addressing Resident Road Concerns | Chief Nourse (Greg Michaud) | Document a process flow for addressing residents' road issues and concerns | 2020-02-02 | 2020-02-02 | Final draft unanimously approved 2/2/2021

## Change Log
Change Date | Initiative | Type of Change | Committee Member Name | Comments
2021-01-05 | Public Peddlers and Food Carts | New Initiative | Phil Wagner
2021-01-05 | Public Peddlers and Food Carts | Assigned | Phil Wagner
2021-01-05 | Bike Racks | Inactive to Active Status | Phil Wagner
2021-01-05 | Bike Racks | Assigned | Phil Wagner
2021-01-05 | Lower Main Street Beautification | New Initiative | Sally Walsh
2021-01-05 | Lower Main Street Beautification | Assigned | Sally Walsh
2021-01-05 | Active Living Committee Liaison | New Ongoing | Doug Leland
2021-01-05 | Active Living Committee Liaison | Assigned | Doug Leland | Responsibilities will change when Active Living Committee is sunsetted 6/21
2021-01-05 | Maintain Complete Streets Policy | New Ongoing | Doug Leland
2021-01-05 | Maintain Complete Streets Policy | Assigned | Doug Leland | Will take on short term; to be transitioned
2020-12-05 | Write and Submit Complete Streets Policy | Completed | Doug Leland
2021-02-02 | Document a process flow for road concerns | Completed | Greg Michaud
2021-03-02 | Multi-use Path - Mallett to US-1 | New Initiative | Liz McDonald | in collaboration with Connect Freeport
2021-03-02 | Multi-use Path - Mallett to Pine Tree | New Initiative | Liz McDonald | in collaboration with Connect Freeport
2021-03-02 | Multi-use Path - Desert to LLBean Dist | New Initiative | Liz McDonald | in collaboration with Connect Freeport
2021-03-02 | Multi-use Path - Yarmouth to downtown | New Initiative | Liz McDonald | in collaboration with Connect Freeport
2021-03-02 | Taxi Stand Repurpose | New Initiative | Phil Wagner
2021-03-02 | Multi-use Path - Mallett to US-1 | Assigned | Liz McDonald
2021-03-02 | Multi-use Path - Mallett to Pine Tree | Assigned | Liz McDonald
2021-03-02 | Multi-use Path - Desert to LLBean Dist | Assigned | Liz McDonald
2021-03-02 | Multi-use Path - Yarmouth to downtown | Assigned | Liz McDonald
2021-03-02 | Taxi Stand Repurpose | Assigned | Phil Wagner

## Committee Members
Committee Members as of April 6, 2021
Committee Member | Address | Contact |  | Term Expiration | Role | Former Member
Greg Michaud | 106 Tenpenny Street | mishes@comcast.net | (207) 522-0453 | 2021-09-01 | Chair
Doug Leland | 29 Cushing Briggs Road | doug@dougleland.com | (207) 522-7620 | 2023-09-01 | Vice Chair
Doug Reighley | 2 Harbor Ridge Road | dreighley@freeportmaine.com |  | Appointed Annually | Town Council Liaison
Adam Bliss |  | abliss@freeportmaine.com | (207) 865-4743 x106 | Indefinite | Staff Lead and Town Engineer
Nate Goodman | 16 Main Street | ngoodman@freeportmaine.com |  | Indefinite* | Acting Police Chief | Sue Nourse
Andrew (Andy) Seymour | Casco Street | aseymour@llbean.com | (207) 671-6502 | Indefinite* | LL Bean Representative | Dave Lockman
Sarah (Sally) Walsh | 24 Lanes Island Way | swalshcpnp@gmail.com | (617) 633-0295 | 2022-09-01 | Member | Geralyn Campanelli
Phil Wagner | 8 Dennison Avenue | phil@pwags.org | (207) 653-7852 | 2023-09-01 | Member | Chester Goggins
Liz McDonald | 130 Dune Drive | emac31810@gmail.com | (858) 204-7128 | 2023-09-01 | Member | Jerry Antl
Barbara Guffin | 70 South Street | bjguffin@gmail.com | (207) 233-3050 | 2023-09-01 | Member | Jamel Torres
*Terms for Police Chief & LL Bean Representative are indefinite as per Admin Code Sec. 614
Previous Committee Members
Susan Nourse | 16 Main Street |  |  | Indefinite | Police Chief
Jerry Antl | 49 Bailey Farm Road |  | 865-6716 | 2023-09-01
Jamel Torres | 8 South Street #2 |  |  | 2023-09-01
Geralyn Campanelli | 201 Grant Road |  | 205-4598 | 2020-09-30
Chester Goggins | 5 Whispering Pines |  | 865-1514 | 2021-09-20
Dave Lockman | Casco Street |  |  |  | LL Bean Representative
Catrina Milliman | 19 Holbrook Street #14

## Attendance
2021 Complete Streets Monthly Meeting Attendance
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Greg Michaud | bar: JAN to MAR
Doug Leland | bar: JAN to MAR
Doug Reighley | bar: JAN to MAR
Adam Bliss | bar: JAN to MAR
Nate Goodman | bar: JAN to MAR
Andrew (Andy) Seymour | bar: JAN to MAR
Sarah (Sally) Walsh | bar: JAN to MAR
Phil Wagner | bar: JAN to MAR
Liz McDonald | JAN: n/a; FEB: X; MAR: X
Barbara Guffin | JAN: n/a; FEB: X; MAR: X